- What needs to be done?

Sample Task List

Prepared for large Championship timed for January

| Task | June | July | Aug | Sept | Oct | Nov | Dec | Jan |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Progress Meetings | ( | ( | ( | ( | ( | ( | ( |  |
| Sponsors Liaison Meeting |  | ( |  | ( | ( |  |  |  |
| Liaison with Council |  |  | ( |  | ( |  |  |  |
| Prepare Budget |  |  | ( |  |  |  |  |  |
| Design contest logo |  |  |  |  |  |  |  |  |
| Prepare documents for Sponsor |  |  | ( |  |  |  |  |  |
| Approach and confirm minor sponsors | ( | ( | ( | ( | ( |  |  |  |
| Council permit application |  |  | ( |  |  |  |  |  |
| Liquor license application |  |  |  |  |  | ( |  |  |
| Select YNZ approved Race Officer |  |  |  | ( |  |  |  |  |
| Prepare preliminary Notice of Race |  | ( |  |  |  |  |  |  |
| Obtain club mailing list from YNZ |  | ( |  |  |  |  |  |  |
| Prepare Notice of Race |  |  | ( |  |  |  |  |  |
| Submit Notice of Race to YNZ for approval |  |  |  | ( |  |  |  |  |
| Mail out Notice of Race |  |  |  | ( |  |  |  |  |
| Newsletter |  |  |  | ( |  |  |  |  |
| Reminder to clubs of closing date |  |  |  |  |  |  | ( |  |
| Confirmation of entries to skippers |  |  |  |  |  |  |  | ( |
| Contact boat owners for rescue boats duties |  |  |  |  | ( |  |  |  |
| Order T-Shirts |  |  |  |  |  | ( |  |  |
| Organise speakers for prizegiving etc |  |  |  |  |  | ( |  |  |
| Invite dignitaries for opening/closing ceremony |  |  |  |  |  | ( |  |  |
| Complete event report for YNZ and Sponsors |  |  |  |  |  |  |  | ( |
| Print certificates |  |  |  |  |  | ( |  |  |
| Arrange sailmaker/chandlers to be available |  |  |  |  |  |  | ( |  |
| Arrange after match socials |  |  |  |  |  | ( |  |  |
| Prepare official notice board |  |  |  |  |  |  | ( |  |
| Prepare sign on/off sheets |  |  |  |  |  | ( |  | ( |
| Prepare Risk Management Plan |  |  |  |  |  |  |  |  |
| Arrange security |  |  |  |  |  |  | ( |  |
| Prepare and have approved Sailing Instructions |  |  |  | ( | ( | ( |  |  |
| Advise harbour authority |  |  |  |  |  |  | ( |  |
| Arrange protest committee |  |  |  |  |  | ( |  |  |
| Arrange committee boats |  |  |  |  |  | ( |  |  |
| Arrange flags etc |  |  |  |  |  |  | ( |  |
| Book venue for measuring |  |  |  |  | ( |  |  |  |
| Arrange jigs etc |  |  |  |  |  | ( |  |  |
| Arrange Marquees |  |  |  |  | ( |  |  |  |
| Arrange Coolstore |  |  |  |  | ( |  |  |  |
| Arrange Portaloos |  |  |  |  | ( |  |  |  |
| Arrange Furniture |  |  |  |  |  | ( |  |  |
| Arrange Signage |  |  |  |  |  |  | ( |  |
| Arrange Flagpoles |  |  |  |  |  | ( |  |  |
| Arrange Burgees |  |  |  |  |  |  | ( |  |
| Arrange Ramps |  |  |  |  |  | ( |  |  |
| Arrange food caravans |  |  |  |  | ( |  |  |  |
| Arrange Kitchen facilities |  |  |  |  |  | ( |  |  |
| Arrange extra electricity/ phone lines |  |  |  |  | ( |  |  |  |
| Arrange wash down hoses |  |  |  |  |  | ( |  |  |
| Arrange PA system |  |  |  |  |  |  | ( |  |
| Arrange boat storage area |  |  |  |  |  |  |  | ( |
| Arrange traffic controls |  |  |  |  |  |  | ( |  |
| Arrange welcome packs |  |  |  |  |  | ( |  |  |
| Information desk |  |  |  |  |  |  |  | ( |
| Recover trophies from last winner |  |  |  |  |  |  | ( |  |
| Arrange photographer for prizegiving |  |  |  |  |  | ( |  |  |
| Grog supplies |  |  |  |  |  |  | ( |  |
| Catering supplies |  |  |  |  |  |  |  | ( |
| Press releases |  |  |  | ( |  | ( | ( | ( |
| Advise close residents |  |  |  |  |  | ( |  |  |
| Prepare programme |  |  |  |  | ( | ( |  |  |
| Programme to print |  |  |  |  |  |  | ( |  |
| Signpost directions |  |  |  |  |  |  | ( |  |
| Personnel Roster -On Water |  |  |  |  |  |  |  | ( |
| Personnel Roster -Site Preparation |  |  |  |  |  |  |  | ( |
| Personnel Roster -Measuring |  |  |  |  |  | ( |  |  |
| Personnel Roster -Bar |  |  |  |  |  |  | ( |  |
| Personnel Roster -Catering |  |  |  |  |  |  | ( |  |
| Personnel Roster -Cleaning |  |  |  |  |  |  | ( |  |
| Personnel Roster -Registration |  |  |  |  |  |  | ( |  |
| Personnel Roster -Rescue boats |  |  |  |  |  | ( |  |  |
| Personnel Roster -Beach warden |  |  |  |  |  |  | ( |  |
| Personnel Roster -On shore officials |  |  |  |  |  | ( |  |  |
| Personnel Roster -Spectator craft |  |  |  |  |  |  | ( |  |
| Personnel Roster -Final clear up |  |  |  |  |  |  | ( |  |